## Project Summary
Project | Aqua Runtime Control Enforcement
Version | 1.1
Team | ELC Cloud Security
Author | Mihirkumar Jani
Reviewer By | Omar Salama / Kannan kuppusamy / Felix Jebamani
Approved By | Abedi Jamshid
Reviewed Date

## Project Plan
ELC - Aqua Runtime Enforcement Project Plan
Phase - 1 - Action Plan
Sr No | Project Task | Detail | Timeline | Start Date | End Date | Action item | Remarks | Duration
1 | SNOW Exemption template document | Document - WIP | 1 Week |  |  | Internal review
2 | Aqua Runtime Exemption tracker template | Document - WIP | 1 Week |  |  | Internal review
3 | Total no of clusters without Runtime enforcement mode | 118 | Done
4 | Identify less critical AKS cluster | 13 Non-Prod AKS clusters | Done |  |  |  | ELCSRE-47554
5 | Number of controls to be enforced | 1 |  |  |  | Analysing Audit Reports
6 | How many clusters we are going to enforce - Phase 1 | 1 |  |  |  | Analysing Audit Reports
7 | Audit Report - behaviour pattern of the Cluster / control | Report | 1 Month | 2024-11-05 | 2024-12-15
8 | Discussion with DevSecOps team on the Runtime Enforcement of control | Discussion with stakeholder | 1 Week | 2024-12-15 | 2024-12-24
9 | Discussion with CloudOps team on the Runtime Enforcement of control | Discussion with stakeholder | 1 Week | 2025-01-03 | 2025-01-10
10 | Discussion with SRE team on the Runtime Enforcement of control | Discussion with stakeholder | 1 Week | 2025-01-03 | 2025-01-10
11 | Confirmation from the SRE team on the Runtime Enforcement of the control on the AKS cluster | Confirmation
12 | Discussion with the AKS cluster owner / Application owners to get the confirmation | Discussion with stakeholder | 1 Week | 2025-01-10 | 2025-01-20
13 | Confirmation from the Application owner on the Runtime Enforcement of the control on the AKS cluster | Confirmation
14 | Remediate all events and make the AKS cluster clean | Remediate |  | 2025-01-13 | 2025-01-25
15 | SNOW template exemption - Flow | Exemption |  | 2025-01-10 | 2025-01-20
16 | ServiceNow / Change order ticket of the activity | Change CAB approval | 1 Week | TBD
17 | Enable enforce mode on the Aqua control on the less critical AKS cluster | Enable enforce mode | TBD | TBD
18 | Keep the added AKS cluster under observation | Under observation | 1 Month | TBD
19 | Take immediate necessary actions if required | Exemption
20 | Rollback plan: | Rollback plan
21 | Move the control of the policy from Enforce to Audit mode | Rollback plan
22 | Informe and update to AKS cluster owner / Application owner | Rollback plan
23 | If required, will do rollback | Rollback | Immediately

## phase wise approach
Sr.No | Phase | AKS cluster name | Environment | Severity | AKS Owner | Application owners | NOTIFICATION DL of the Application | Application details | Number of Applications | Before enforcement - Performance of the AKS (CPU & Memory) (1 month) | After enforcement - Performance of the AKS (CPU & Memory) | Controls enforced | Change Order | Change Approved Date | Change Time Window | SNOW Exemption | Exemption Detail
1 | Phase I | AKS-AP-SoutheastAsia-QA-CLR | Non-prod | Less Critical |  | Harris, Jeremy | alenzi_ext@estee.com; fvieira@estee.com, ClinicalReality.Support@estee.com | CLR
2 |  | AKS-EU-WestEurope-NP-EWP-01 | Non-prod |  |  | khopkins@estee.com | ncaravia@estee.com | Excess Web Inventory
3 |  | AKS-EU-uksouth-QA-CLR | Non-prod |  |  | Harris, Jeremy | alenzi_ext@estee.com; fvieira@estee.com, ClinicalReality.Support@estee.com | CLR
4 |  | AKS-AM-EastUS-NP-SWT | Non-prod |  |  | sweigand@estee.com | sweigand@estee.com | ShawnTests
5 |  | AKS-AM-EastUS-NP-SWTW | Non-prod |  |  | sweigand@estee.com | sweigand@estee.com | ShawnTests
6 |  | AKS-AM-EastUS-NP-DSF1 | Non-prod |  |  | rholt@estee.com | data-science-framework-admins@estee.com | Data Science Framework
7 |  | AKS-AM-EastUS-NP-DSF01 | Non-prod |  |  | rholt@estee.com | rholt@estee.com | Data Science Framework
8 |  | AKS-AM-EastUS-Dev-GMP | Non-prod |  |  | ptan@estee.com | elc-grp@estee.com, cpowell@elc.estee.com | GMP
9 |  | AKS-AM-EastUS-Dev-QRP | Non-prod |  |  | Wong, Ricky | rpetrosy@estee.com | QRPlatform
10 |  | AKS-AM-EastUS-NP-AAI | Non-prod |  |  | gmelkumo@estee.com | gmelkumo@estee.com | AbacusAI
11 |  | AKS-AM-EastUS-NP-LMD | Non-prod |  |  | ishpak@estee.com | jpaulsen@estee.com | LMD Admin
12 |  | AKS-AM-EastUS-NP-DIP | Non-prod |  |  | taungon@estee.com | dteportal@estee.com | DTE Internal Portal
13 |  | AKS-AM-EastUS-NP-DOG | Non-prod |  |  | eepstein@estee.com | adubniko@ru.estee.com | DatadogAutomation

## Weekly events analysis
|  | Week 1 |  | Week 2 |  | Week 3 |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 1 |  | Week 2 |  | Week 3
Sr No | Clusters / Controls | Block Non-compliant Images | Images | Block Non-compliant Images | Images | Block Non-compliant Images | Images | Block Unregistered Images | Images | Block Unregistered Images | Images | Block Unregistered Images | Images | Drift Prevention | Images | Drift Prevention | Images | Drift Prevention | Images
1 | AKS-EU-WestEurope-NP-EWP-01 | 0 | 0 | 2 | 1 | 4 | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2 | AKS-AM-EastUS-NP-SWTW | 2 | 1 | 22 | 5 | 28 | 7 | 0 | 0 | 8 | 3 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
3 | AKS-AM-EastUS-NP-LMD | 19 | 5 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | AKS-AM-EastUS-NP-DIP | 30 | 3 | 2 | 1 | 3 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
5 | AKS-AP-SoutheastAsia-QA-CLR | 34 | 5 | 5 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | AKS-AM-EastUS-NP-DSF1 | 44 | 3 | 5 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | AKS-EU-uksouth-QA-CLR | 48 | 5 | 10 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
8 | AKS-AM-EastUS-Dev-GMP | 48 | 6 | 14 | 4 | 3 | 2 | 0 | 0 | 9 | 7 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0
9 | AKS-AM-EastUS-Dev-QRP | 62 | 5 | 6 | 2 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | AKS-AM-EastUS-NP-DSF01 | 90 | 10 | 11 | 4 | 11 | 3 | 12 | 10 | 11 | 11 | 38 | 12 | 0 | 0 | 0 | 0 | 0 | 0
11 | AKS-AM-EastUS-NP-DOG | 1938 | 1 | 1974 | 3 | 1968 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
12 | AKS-AM-EastUS-NP-SWT | 2046 | 6 | 1930 | 6 | 1966 | 1 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | AKS-AM-EastUS-NP-AAI | 2282 | 9 | 1868 | 3 | 1103 | 3 | 5 | 1 | 7 | 1 | 1 | 1 | 23579 | 3 | 12587 | 1 | 7244 | 1
14 | Total | 6642 |  | 5852 |  | 5100 |  | 17 |  | 40 |  | 103 |  | 23579 |  | 12587 |  | 7244
Week 1 | 05-11-2024 01:01:14 PM to 12-11-2024 12:55:39 AM
Week 2 | 11-11-2024 10:34:51 PM to 18-11-2024 12:59:36 PM
Week 3 | 18-11-2024 01:01:15 PM to 25-11-2024 12:59:57 AM